## Love Tennis team leads
Area | Lead | Key Responsibility | Email
Event Lead |  | Overall delivery
Marketing Lead |  | Socials + promotion
Activities Lead |  | On/off court setup
Volunteer Lead |  | Rosters + support
Welcome/Registration |  | Data capture + sign-ups
Follow-Up Lead |  | Post-event contact

## Planning Tracker
Week | Focus Area | Key Tasks | Marketing & Social Media | Owner | Status
8 weeks out | PLAN | Build Dream Team (roles + volunteers) | Announce Love Tennis date on socials
7 weeks out | PLAN | Set budget + confirm event plan | Create Facebook event
6 weeks out | PLAN | Confirm activities + layout + equipment | First promo post + email to members
5 weeks out | PLAN | Club BUZZ night. Food & refreshments, fun & social for all members | Comms to all members
5 weeks out | PROMOTE | Connect with schools + community groups | Posters + community outreach
4 weeks out | PROMOTE | Lock in food, entertainment, MC | Social post (activities preview)
3 weeks out | PROMOTE | Confirm volunteers + rosters | Member push: bring a friend
2 weeks out | PROMOTE | Finalise offers (joining + coaching) | Boost posts / ads
1 week out | FINAL PUSH | Confirm roles, equipment, signage | Daily countdown posts
Event Day | DELIVER | Run event + capture data | Live posts and stories
1–2 days after | FOLLOW UP | Send data + thank volunteers | Thank you post
Week after | FOLLOW UP | Contact all visitors | Promote join offers
2–4 weeks after | RETAIN | Invite back to programmes/BBQ/event/etc | Share photos + success stories