## Asset Renewals & Maintenance
Sample Renewals and Maintenance Plan for a Tennis Club
Notes
(1). The tables below are a guide only and we recommend that you get timely quotes from professionals for each task. (2). The 'today cost' column is an estimate only and is a guide to help you budget. (3). Use the quote column to keep a record of quotes for your renewals & maintenance over the years. It will help you in times to come. (4). The priority column is our recommendation on when you should complete the renewal or maintenace task. It is based on Ren and Age. (5). Ren is the last time the asset was renewed, improved or maintained. Or when it was built. (6). The years column is a useful planning tool so you can schedule your renewals and maintenance accurately and effectively.
Estimated Asset Renewal Cost | 1580710
Assets - Detailed | Today Cost | Quote | Priority | Category | Locale | Structure | Type | Area (sq.m) | Ren | Age (yrs) | Notes | Mulitplier
Club House | 960000 |  | As Required | Buildings | Club House | Concrete Block/Timber | Single Level | 320 | 1977 | 45 | Box type single level club house with bar kitchen. Exterior requires painting | 3000
Club House Roof | 48000 |  | Medium | Buildings | Club House | Iron | Pitched | 320 | 1977 | 45 | Shallow angle pitched roof. Requires replacement in next 5-10 years. | 150
Club House Bar/Kitchen | 24000 |  | Medium | Club Assets | Club House | Timber | Fit Out | 16 | 2005 | 17 | Home style kitchen with no extraction. Bar fridge, no beer taps. No chiller. | 1500
Change Room - Male | 144000 |  | Medium | Buildings | Club House | Timber | Male | 36 | 1977 | 45 | Open shower block. 1x Urinal, 1x flush toilet. | 4000
Change Room - Female | 120000 |  | High | Buildings | Club House | Timber | Female | 30 | 1977 | 45 | 2x shower cubicles with curtains. 2x flush toilets. | 4000
Tennis Court 1 | 28152 |  | Medium | Sports Assets | Bay 1 | Astroturf | Playing surface | 625.6 | 2012 | 10 | Individual court cost based on current footprint and includes perimeter areas. | 45
Tennis Court 2 | 28152 |  | Medium | Sports Assets | Bay 1 | Astroturf | Playing surface | 625.6 | 2012 | 10 | Individual court cost based on current footprint and includes perimeter areas. | 45
Tennis Court 3 | 28152 |  | High | Sports Assets | Bay 2 | Hardcourt | Playing surface | 625.6 | 2005 | 17 | Individual court cost based on current footprint and includes perimeter areas. | 45
Tennis Court 4 | 28152 |  | High | Sports Assets | Bay 2 | Hardcourt | Playing surface | 625.6 | 2005 | 17 | Individual court cost based on current footprint and includes perimeter areas. | 45
Tennis Court Light Poles | 7500 |  | As Required | Club Assets | Bay 1 | Steel | Pole | 3 | 1977 | 45 | New pole replacement to current height. | 2500
Tennis Court Light Poles | 3750 |  | As Required | Club Assets | Bay 1 | Steel | Pole | 1.5 | 1977 | 45 | New pole replacement to current height. | 2500
Tennis Court Light Poles | 3750 |  | As Required | Club Assets | Bay 2 | Steel | Pole | 1.5 | 1977 | 45 | New pole replacement to current height. | 2500
Tennis Court Light Poles | 7500 |  | As Required | Club Assets | Bay 2 | Steel | Pole | 3 | 1977 | 45 | New pole replacement to current height. | 2500
Tennis Court Lights | 5790 |  | Medium | Club Assets | Bay 1 | Halogen | Court lights | 6 | 2005 | 17 | LED light replacement to current lux. | 965
Tennis Court Lights | 2895 |  | Medium | Club Assets | Bay 1 | Halogen | Court lights | 3 | 2005 | 17 | LED light replacement to current lux. | 965
Tennis Court Lights | 2895 |  | Medium | Club Assets | Bay 2 | Halogen | Court lights | 3 | 2005 | 17 | LED light replacement to current lux. | 965
Tennis Court Lights | 5790 |  | Medium | Club Assets | Bay 2 | Halogen | Court lights | 6 | 2005 | 17 | LED light replacement to current lux. | 965
Tennis Court Net Posts | 5560 |  | As Required | Sports Assets | All | Aluminium | Insert sleeve | 8 | 2005 | 17 | All courts; 1070mm H x (80mm x 80mm - square) | 695
Tennis Court Nets | 795 |  | As Required | Sports Assets | All | Double Mesh | Full Drop | 5 | 2015 | 7 | All courts; 12.08m court span | 159
Rebo Wall (Volley Wall) | 28862 |  | As Required | Sports Assets | Bay 1 | Stainless Steel, Carpet | Mobile | 1 | 2020 | 2 | Rebo mobile volley system. 5.75m option. Converted from UKPound14995 = $29k, excl shipping | 29000
Perimeter Fences | 64395 |  | As Required | Club Assets | Bay 1 | Steel, Mesh | High | 243 | 1977 | 45 | New fence build and includes gates, supports. | 265
Court Lighting System | 1300 |  | As Required | Club Assets | All | Electronic | Electronic | 1 | 2020 | 2 | Club Spark subsidised by Tennis NZ | 1300
Access Gate | 1300 |  | As Required | Club Assets | Bay 1 | Electronic | Electronic | 1 | 2020 | 2 | Club Spark subsidised by Tennis NZ | 1300
Court Seating | 2500 |  | Low | Club Assets | All | Timber | Portable | 2 | 2002 | 20 | Seating located court side in between bays. Replace with lighter products (see Forza. NetWorldSports.co.nz) | 1250
Walkways/Paths | 11520 |  | As Required | Club Assets | All | Asphalt | Standard | 72 | 2009 | 13 | Total length & width of walkways and paths. Industry standard depth. | 160
Furniture/Equipment | 16000 |  | Low | Club Assets | All | Various | Various | 1 | 2012 | 10 | Includes AED, cleaning equipment, drinking fountains - assets grouped | 16000
Estimated Annual Maintenance Cost | 9310.32
Assets - Detailed | Today Cost | Quote | Maintain Cycle | Category | Task | Structure | Type | Area (sq.m) | Ren | Age | Notes
Club House | 640 |  | Annual | Buildings | Wash | Concrete Block/Timber | Exterior | 320 | 1977 | 45 | Exterior annual building wash. Make repairs as required. | 2
Club House | 4000 |  | Annual | Buildings | Paint & Repair | Timber/Gib Board | Interior | 32 | 1977 | 45 | Set an annual budget for this & target high use areas. Recommend a professional painter. | 125
Club House Roof | 800 |  | Annual | Buildings | Wash | Iron | Pitched | 320 | 1977 | 45 | Exterior annual roof wash. Make repairs as required. Complete with building wash. Paint if required. NB - working at height. | 2.5
Club House Bar/Kitchen | 160 |  | Annual | Club Assets | Deep Clean | Timber | Fit Out | 16 | 2005 | 17 | Deep clean for high use areas. A kitchen hygiene rating maybe required to comply with. | 10
Change Room - Male | 180 |  | Annual | Buildings | Deep Clean | Timber | Male | 36 | 1977 | 45 | Deep clean for high use areas. Schedule this outside of regular clean cycle | 5
Change Room - Female | 150 |  | Annual | Buildings | Deep Clean | Timber | Female | 30 | 1977 | 45 | Deep clean for high use areas. Schedule this outside of regular clean cycle | 5
Tennis Court 1 | 344.08 |  | Annual | Sports Assets | Groom | Astroturf | Playing Surface | 625.6 | 2012 | 10 | Complete this annually or bi-annually. Recommend a professional court groomer | 0.55
Tennis Court 2 | 344.08 |  | Annual | Sports Assets | Groom | Astroturf | Playing Surface | 625.6 | 2012 | 10 | Complete this annually or bi-annually. Recommend a professional court groomer | 0.55
Tennis Court 3 | 344.08 |  | Annual | Sports Assets | Wash | Hardcourt | Playing Surface | 625.6 | 2012 | 10 | Complete this annually or bi-annually. Recommend a professional chemical wash company | 0.55
Tennis Court 4 | 344.08 |  | Annual | Sports Assets | Wash | Hardcourt | Playing Surface | 625.6 | 2012 | 10 | Complete this annually or bi-annually. Recommend a professional chemical wash company | 0.55
Court Seating | 270 |  | Annual | Club Assets | Paint & Repair | Timber | Portable | 2 | 2002 | 20 | Set an annual budget for this or complete at your working bees. | 135
Walkways/Paths | 144 |  | Annual | Club Assets | Wash | Asphalt | Standard | 72 | 2009 | 13 | Exterior annual wash. Complete with building wash or complete at your working bees. | 2
Perimeter Fences | 1590 |  | Annual | Club Assets | Repair | Steel, Mesh | High | 6 | 1977 | 45 | Set an annual budget for this. Recommend a professional fencer. | 265
Furniture/Equipment | 500 |  | Annual | Club Assets | Repair | All | Various | 1 | 2012 | 10 | Includes all equipment & set aside an annual budget | 500
Estimated Long Term Maintenance Cost | 95326
Assets - Detailed | Today Cost | Quote | Maintain Cycle | Category | Task | Structure | Type | Area (sq.m) | Ren | Age | Notes
Club House | 52661 |  | Low (10) | Buildings | Paint & Repair | Concrete Block/Timber | Exterior | 320 | 1977 | 45 | Recommended 10 year paint for cladding. Make repairs as required
Rebo Wall (Volley Wall) | 42665 |  | Low (10) | Sports Assets | Replace Carpet | Stainless Steel, Carpet | Mobile | 14 | 2020 | 2 | Replace front facing felt carpet. Assume at 10 years
These items are estimated to cost as above in 10 years.